## Sheet1
Roadmap Milestone Tracker
DIRECTIONS
1 | Start with one topic at a time
2 | Decide on “key milestones” – not details but big chunks of the work (if you are stuck, you can refer to the worksheet for that topic)
3 | Determine how much time you anticipate needing to meet each milestone you have identified and put that on the worksheet
4 | Please remember: The actual Roadmap device does not matter; If you prefer to use Excel or other project management software, that’s fine. What does matter is laying out your plan to becoming an MTM provider by June, even if it’s starting small. It’s possible that your first milestone will be identifying the population you want to serve and how many meals you want to offer in their first few months of operation.
Each of these topics are what we've identified as the areas that are key to your success; but you may want to add more categories, such as communications and fundraising. Use this as a living document, to make commitments and track progress
Milestone Tracker
Mark progress as you move forward. Milestones can be marked as complete by changing font to bold.
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Public Policy
Client Services
Nutrition
Kitchen
Meal Packaging
Delivery
Volunteer Services
Contracting
| DELIVERABLES DUE | Oct: Narrative for MTM program; Feb: Scope of Work for Contracts - Draft; Mar: Checklists and Roadmap; Apr: Office Hours: Contract Pitch Deck; 3-5 MTM Recipes; SOW Contract (final); Financial Plan; Jun: Office Hours: Financial Plan - Final; Business Plan -Draft
[8 empty] | NYC On-site: Meal photos and eval: Business Plan Outline |  | June 28: Business Plan - Final
| Sample Tracker | Oct: (Milestones marked BOLD = complete)
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
| Public Policy | (Milestones marked BOLD = complete) Oct: Complete contact list; (Milestones marked BOLD = complete) Jan: Meet with all contacts; (Milestones marked BOLD = complete) Mar: Follow up with all contacts
| Client Services | (Milestones marked BOLD = complete) Oct: Decide demographics; (Milestones marked BOLD = complete) Mar: Agree on referral and intake
| Nutrition | (Milestones marked BOLD = complete) Nov: Menu Development
|  |  |  | Assessment/Reassessment |  |  |  | Nutrition Education
| Kitchen | (Milestones marked BOLD = complete) Nov: Kitchen design; (Milestones marked BOLD = complete) Mar: Kitchen build
|  |  |  | Procurement process |  | Inventory plan |  | Cooking procedures
Meal Packaging
Delivery
Volunteer Services
Contracting